## Sprints
PRODUCT BACKLOG
| Sprint | Week | Sprint Goal | Start Date | End Date | Sprint State
| 1 | 2/3 |  | 2022-10-24 | 2022-11-04 | Inactive
| 2 | 4/5 |  | 2022-11-07 | 2022-11-18 | Inactive
| 3 | 6/7 | Discussion on SRS | 2022-11-21 | 2022-12-02 | Closed
MST + Term Break
| 4 | 12/13 | Sqlite Table Concept -added slot -Add get function with serialization -added config.sh framework -Add path check and updating function Edit SRS Remove stray command string Commits on Jul 5, 2023 Merge branch 'ta0u-branch' of https://github.com/ET0735-DevOps-AIoT-A… Dispensing -Update servo.py -Create dispense.py -Create servo.py -Create LCD.py -Create lcd function -added slot | 2023-06-26 | 2023-07-07 | Active
| 5 | 14/15 | Dispenser -Fixed screen overflow dispense.py -Dispense fixes -Fixes to make servo start -Added buzzer and led flashing -updated import Payment -check RFID and other bug fixes -Add stock, and methods to update it -Utility function to beep when there are exceptions -Docstring for SQLite get item -Payment function (SQLite DB, prompt, RFID) [sync] -RFID card reading (blocking fn) [sync, callbacks] burglar alarm added Webpage -Separate functions for auth in its own file | 2023-07-10 | 2023-07-21 | Active
| 6 | 16/17 | Webpage -Add build dir to gitignore -TSConfig -Update deps -Relocate backend var -Cookie -> LocalStorage -useSelector for homepage loginstate -Optimise Imports -Redux for login in MyAppBar -Order page -Order Card UI -Order interface and relevant functions -Use Redux for auth -Dockerfile for containerisation -Change imports, drop .ts -getAllItems in abstract class -Interface OrderReq -Order admin route -Orders route -Reducers with Redux! -Payment success navigation -Navigate to /pay -Change VendingItem to interface -payFor in frontend (POST) -Updates to PayPage (see desc) -Separate ErrResult to handle all error cases -Add CardDetails and bearer -Add /orders -Add VendingItem -Add PayPage -Add Shop + Onboarding for HomePage -Separate auth and vending into own files -Pay after select -Update stock -Move import to func -Run Python file when startup is selected -Init inventory, use "slots" -Dispensing optimisations -added bash.sh overall file -Interface payment with dispense -TSConfig -Update deps -useSelector for homepage loginstate | 2023-07-24 | 2023-08-04 | Active
| 7 | 17/18 | Updates on websocket and keypad -Changed Pi from Server to Client -Update and rename websocket_vendingmachine.py to websocket_client.py -Update websocket_vendingmachine.py -Pushed websocket_vendingmachine.py -MachV2.sh implemented -Updated .sh file with new exit codes í°³ -live updates and stops listener -Add code to run thread -Keypad Interfacing code | 2023-08-07 | 2023-08-18 | Active
Formulas:
End Date = [Start Date]+11
Start Date = [Start Date, row above]+14

## Active Sprint Board (hidden)
To Do | Doing | Done

## Product Backlog
ID | Story Title | Story Description | Definition of Done | Estimated Effort (hours) | Actual Effort (hours) | Status | Sprint
1 | Create Use Case Diagrams in SRS document | As a Software Developer, I need to define all the different Use Case Diagrams for the Automated Checkout System | All necessary Use Case Diagrams are defined in the SRS document SRS document is commited and pushed to Github | 4 | 5 | To Do | Sprint 1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95 | [5 empty] | Doing
96
97
98
99
100

## enum (hidden)
Sprint | Start Date | End Date | Story Status | Spint State
Sprint 1 |  |  | To Do | Inactive
Sprint 2 |  |  | Doing | Active
Sprint 3 |  |  | Done | Closed
Sprint 4
Sprint 5
Sprint 6